## Лист1
|  |  | Daria Shushkova |  | Mohamed Amer |  | Andrey Sysoev |  | Sadim Badham
# | task | short summory | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date)
1 | task1 | Create 3d parts for the Vehicle | Create holders for battery/breadboard(22.04.25) | Done 21.04.25 | Create holders for motors(22.04.25) | Done 21.04.25 | Create holders for IR sensors(22.04.25) | Done(20.04.25) | Create holders for Ultrasonic Senors(22.04.25) | Done(21.04.25)
2 | task2 | Create SYSML Diagrams | Create pre final version of the system and TinkerCad Sim. Sequence Diagram, State Machine Diagram, Use Case Diagram(27.04.25) | Done 25.04.25 | Create Activity Diagram, Internal Block Diagram(27.04.25) | Done 25.04.25 | Create Requirement Diagram, Parametric Diagram(27.04.25) | Done 25.04.25 | Create Block Definition Diagram, Package Diagram(27.04.25) | Done 25.04.25
3 | task3 | Final versions of SYSML Diagrams, Realization of prototypes. | Update Sequence Diagram, State Machine Diagram, Use Case Diagram(04.05.25). Add comments, update variables. | Updated Sequence Diagram, State Machine Diagram, Use Case Diagram(Done 03.05.2025). Added comments, update variables(Done 04.05.2025) | Update Activity Diagram, Internal Block Diagram(04.05.25) | Done 03.05.25 | Update Requirement Diagram, Parametric Diagram.Optimise state machine, add logic for obsiticale avoidance(04.05.25) | Done 04.05.25 | Update Definition Diagram, Package Diagram(04.05.25) | Done 03.05.25
4 | task4 | Documentation of components, build system with components, check the voltage of components. | Measurement voltage and current of components in Tinkerkad(11.05.25), participating in building of system (wiring, connections, main code adjusting after testing)(Done 12.05.25) | Measurement voltage and current of components in Tinkercad(Done 10.05.25), perticipation in building of system (wiring, connections, main code adjusting after testing)(Done 12.05.25) | Uplode datasheets of componets via internet, build system with components(11.05.25) | Done 10.05.25 | Measurement voltage and current(in Multisim,Tinkercad),helping with building of system(11.05.25) | Done 11.05.25 | Helping building of system(11.05.25) | Done 11.05.25
5 | task5 | Test modules(Measurement protocol, construction of system, development of software unit tests), Modularize the system (01.06.25) | Documenting: Measurement protocol of Ir,Ultrasonic Sensors and motor controller. Logging outputs of tested components, wiring manangment, connecting components, main code adjusting after testing (01.06.25) | Done 31.05.25 | Building of system, unit tests,modularization of a system(01.06.25) | Done 31.05.25 | Measurment of voltage, wire management, unit test(01.06.25) | Done 01.06.25 | Update readme documentation, create loigc for colour sensor, test colour sensor(01.06.25) | Update readme documentation(25.05.25), create logic for colour sensor(01.06.25)
6 | task6,7 | Ensure that system is working corectly, refine state machine in UPPAAL(add guards and invariants)(08.06.25), optimizing speed of vehicle(08.06.25)