## Лист1
|  |  | Daria Shushkova |  | Mohamed Amer |  | Andrey Sysoev |  | Sadim Badham
# | task | short summory | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date)
1 | task1 | Create 3d parts for the Vehicle | Create holders for battery/breadboard(22.04.25) | Done 21.04.25 | Create holders for motors(22.04.25) | Done 21.04.25 | Create holders for IR sensors(22.04.25) | Done(20.04.25) | Create holders for Ultrasonic Senors(22.04.25) | Done(21.04.25)
2 | task2 | Create SYSML Diagrams | Create pre final version of the system and TinkerCad Sim. Sequence Diagram, State Machine Diagram, Use Case Diagram(27.04.25) | Done 25.04.25 | Create Activity Diagram, Internal Block Diagram(27.04.25) | Done 25.04.25 | Create Requirement Diagram, Parametric Diagram(27.04.25) | Done 25.04.25 | Create Block Definition Diagram, Package Diagram(27.04.25) | Done 25.04.25
3 | task3 | Final versions of SYSML Diagrams, Realization of prototypes. | Update Sequence Diagram, State Machine Diagram, Use Case Diagram(04.05.25). Add comments, update variables. | Updated Sequence Diagram, State Machine Diagram, Use Case Diagram(Done 03.05.2025). Added comments, update variables(Done 04.05.2025) | Update Activity Diagram, Internal Block Diagram(04.05.25) | Done 03.05.25 | Update Requirement Diagram, Parametric Diagram.Optimise state machine, add logic for obsiticale avoidance(04.05.25) | Done 04.05.25 | Update Definition Diagram, Package Diagram(04.05.25) | Done 03.05.25