## Лист1
|  |  | Daria Shushkova |  | Mohamed Amer |  | Andrey Sysoev |  | Sadim Badham
# | task | short summory | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date) | ToDo(with Deadline) | Done(Incl finishing date)
1 | task1 | Create 3d parts for the Vehicle | Create holders for battery/breadboard(22.04.25) | Done 21.04.25 | Create holders for motors(22.04.25) | Done 21.04.25 | Create holders for IR sensors(22.04.25) | Done(20.04.25) | Create holders for Ultrasonic Senors(22.04.25) | Done(21.04.25)
2 | task2 | Create SYSML Diagrams | Create pre final version of the system and TinkerCad Sim. Sequence Diagram, State Machine Diagram, Use Case Diagram(27.04.25) | Done 25.04.25 | Create Activity Diagram, Internal Block Diagram(27.04.25) | Done 25.04.25 | Create Requirement Diagram, Parametric Diagram(27.04.25) | Done 25.04.25 | Create Block Definition Diagram, Package Diagram(27.04.25) | Done 25.04.25
3 | task3 | Final versions of SYSML Diagrams, Realization of prototypes. | Update Sequence Diagram, State Machine Diagram, Use Case Diagram(04.05.25). Add comments, update variables. | Updated Sequence Diagram, State Machine Diagram, Use Case Diagram(Done 03.05.2025). Added comments, update variables(Done 04.05.2025) | Update Activity Diagram, Internal Block Diagram(04.05.25) | Done 03.05.25 | Update Requirement Diagram, Parametric Diagram.Optimise state machine, add logic for obsiticale avoidance(04.05.25) | Done 04.05.25 | Update Definition Diagram, Package Diagram(04.05.25) | Done 03.05.25
4 | task4 | Documentation of components, build system with components, check the voltage of components. | Measurement voltage and current of components in Tinkerkad(11.05.25), participating in building of system (wiring, connections, main code adjusting after testing)(Done 12.05.25) | Measurement voltage and current of components in Tinkercad(Done 10.05.25), perticipation in building of system (wiring, connections, main code adjusting after testing)(Done 12.05.25) | Uplode datasheets of componets via internet, build system with components(11.05.25) | Done 10.05.25 | Measurement voltage and current(in Multisim,Tinkercad),helping with building of system(11.05.25) | Done 11.05.25 | Helping building of system(11.05.25) | Done 11.05.25
5 | task5 | Test modules(Measurement protocol, construction of system, development of software unit tests), Modularize the system (01.06.25) | Documenting: Measurement protocol of Ir,Ultrasonic Sensors and motor controller. Logging outputs of tested components, wiring manangment, connecting components, main code adjusting after testing (01.06.25) | Done 31.05.25 | Building of system, unit tests,modularization of a system(01.06.25) | Done 31.05.25 | Measurment of voltage, wire management, unit test(01.06.25) | Done 01.06.25 | Update readme documentation, create loigc for colour sensor, test colour sensor(01.06.25) | Update readme documentation(25.05.25), create logic for colour sensor(01.06.25)
6 | task6,7 | Ensure that system is working corectly, refine state machine in UPPAAL(add guards and invariants)(08.06.25), optimizing speed of vehicle(08.06.25) | For upper-level states: refined system-level state machine into timed automata using UPPAAL. Added guards and invariants to model timing constraints. Verified system reactions (sensor checks, motor updates, etc.) against implementation logic. Simulated the model in UPPAAL. Exported and committed the UPPAAL XML model to Git for version tracking. Finalizing overall UPPAAL model after obstacle avoidannce implementation. | Done 08.06.25 |  |  | For obstacle avoidance sub-states: Refined system-level state machine into timed automata using UPPAAL. Added guards and invariants to model timing constraints. Verified system reactions (sensor checks, motor updates, etc.) against implementation logic. Simulated the model in UPPAAL. Exported and committed the UPPAAL XML model to Git for version tracking. | Done 07.06.25
7 | task8 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (13.06.25) | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions, documenting sensors output in log file and upload it to Git) (13.06.25) | Done 13.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions, upload the latest working result to Git) (13.06.25) | Done 13.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (13.06.25) | Done 13.06.25
8 | task9 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (16.06.25) | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (16.06.25) | Done 16.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions, upload the latest working result to Git) (16.06.25) | Done 16.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (16.06.25) | Done 16.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (16.06.25) | Done 16.06.25
9 | task10 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (20.06.25) | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions) (20.06.25) | Done 20.06.25 | Testing the system (working on unit tests, testing state machine, motor configuration, sensors reactions, upload the latest working result to Git) (20.06.25) | Done 20.06.25
10 | task11 | Creating final presentation (22.06.25) | Working on the contentent of final presentation (22.06.25) | Done 22.06.25 | Working on the design of the final presentation (22.06.25)
11 | task12 | Updating State Machine and Sequence Diagram, and the main code (22.06.25) | Updating State Machine and Sequence Diagram, and the main code based on testing (22.06.25) | Done 22.06.25 |  |  |  |  | Help with color sensors implementation (22.06.25) | Done 15.06.25